NeuroImage paper: phased research plan

CIDUR-based methods manuscript — AI/automation-inspired acquisition standards & DBI

This document breaks the remaining work into phases with activities, owners, dependencies, and concrete deliverables. “AI-assisted” means collaborative work with coding and drafting support; “Research team” means institutional accountability, ethics, execution on restricted systems, and final scientific approval.

# Executive summary

Phases 0–2: scope, ethics constraints, DBI v1 spec, audit code, first results (Table 1 / Figure 1).

Phase 3 (required for v1): dcm2niix batch proof → Table 2 / Figure 2 as planned.

Phase 4 (optional): human-label validation for classification accuracy if claimed.

Phases 5–7: full manuscript, supplement, reproducibility package, internal review, submission, revision.

Future (not v1 paper): versioned BIDS conversion heuristics + bids-validator; correlate DBI with validator severity.

# Role split (reference)

## AI-assisted (end-to-end support)

Narrow NeuroImage story: 1–3 claims, article type (methods vs original), figure/table plan.

Operationalize DBI: explicit rules, scoring rubric, pseudocode, Python on CIDUR_data.

Audit pipeline: DICOM tree walk, tag extraction, missing-field flags, series classification rules, scanner-stratified summaries.

Required for v1: batch dcm2niix (pinned version), log success/warnings, pass/fail definition → Table 2.

Draft sections: Introduction framing, Methods, Results skeleton, Discussion (limits, related work).

Supplement drafts: SOP excerpts, extra tables, validator specification.

Reproducibility package: README, config template, rerun instructions (within policy).

## Research team only

IRB / consent / data use: what may be described, shared, or placed in a public repository.

Authorship order, competing interests, funding statements, final approval of all text.

Running heavy or queued jobs on institutional systems when automation cannot execute here.

NeuroImage portal: submission, cover letter, revisions, reviewer responses.

Ground truth for ambiguous DICOM: protocol truth, manual labels for validation subsets.

# Prerequisites from the team (start Phase 0)

LOCKED (update if changed): (a) Public release of both code and statistics; validator packaged in the spirit of bids-validator.

(b) Cohort = CIDUR_data after de-identification to sub-0001, sub-0002, …; cite final N after exclusions.

(c) Primary outcomes = DBI audit + dcm2niix batch proof (both required for v1; pin dcm2niix version in Methods).

(d) Full BIDS layout + bids-validator vs DBI → explicit future work (not required for v1 submission).

(e) Optional: 20–50 series folders with human-assigned modality/role labels for classification accuracy.

(f) Optional: prospective cleaning-time logs — not required for core claims.

# Data and tooling assumptions

Primary imaging root: CIDUR_data (XNAT-style EP*/EP*/*_MR_*/scans/.../DICOM).

Supporting artifacts: vecta/ (DOCX generators, phased plan, future audit/DBI scripts).

Empirical claims in the paper must cite the frozen code version and cohort snapshot used for numbers.

# Phase 0 — Scope, governance, and story lock

Goal: one-page agreement so later phases do not rework direction.

| Activity | Owner | Deliverable / output |
| --- | --- | --- |
| Confirm cohort N and IRB-permitted descriptions | Research team | Email memo or protocol excerpt: allowed claims, sharing tier |
| Choose article type (methods-primary vs original with methodological core) | Team + AI-assisted | Half-page decision note |
| Write 1–3 primary claims + 3–5 secondary claims | Team + AI-assisted | Claims sheet (bulleted) |
| Figure/table plan (draft list with purpose per panel) | AI-assisted + team sign-off | Figure plan document (e.g., Fig1 audit by scanner, Fig2 DBI components) |
| Confirm v1 outcomes: DBI + dcm2niix only (no other converters in scope) | Research team | Locked outcome paragraph; optional preregistration |

Exit criteria: signed-off claims + figure list + sharing tier + explicit DBI + dcm2niix outcome plan.

Estimated effort (team): 0.5–2 sessions; (AI-assisted): 1 iteration on drafts.

# Phase 1 — DBI v1 formal specification

Goal: reproducible definition of Data Birth Integrity for this study (not necessarily final forever).

| Activity | Owner | Deliverable / output |
| --- | --- | --- |
| List DBI components (e.g., metadata completeness, naming, gradient integrity for DWI, spatial, drift) | AI-assisted draft + team edit | DBI v1 spec (Markdown or DOCX subsection) |
| Per component: binary pass/fail vs 0–1 score; weights if composite | Team decision | Scoring table in spec |
| Per-modality minimum rules (which components apply to which series types) | Team + AI-assisted | Modality × component matrix |
| Pseudocode for session-level and series-level aggregation | AI-assisted | Appendix for Methods / supplement |

Exit criteria: frozen DBI v1.0 document with version date and changelog stub.

Dependencies: none beyond Phase 0 lock — dcm2niix is in scope for v1 alongside DBI.

# Phase 2 — Audit pipeline implementation and primary results

Goal: run on full MR session set; produce Table 1 + Figure 1 for the paper.

| Activity | Owner | Deliverable / output |
| --- | --- | --- |
| Python package: walk CIDUR_data, one record per scan folder or per series sample | AI-assisted; team runs if needed | cidur_audit/ or vecta/cidur_dbi/ with requirements.txt |
| Extract DICOM tags for checklist; handle transfer syntax / read failures | AI-assisted | Logged exceptions per file |
| Assign scanner cluster (manufacturer, model, field) | AI-assisted | Column in per-series CSV |
| Compute DBI v1 subscores and composite | AI-assisted | per_series.csv, per_session.csv summaries |
| Scanner-stratified tables and plots | AI-assisted + team QC | Table 1 (LaTeX/Word) + Figure 1 (e.g., stacked bars or heatmap) |
| Spot-check 10–20 random series against console or second reader | Research team | Short QC log |

Exit criteria: frozen results files + figure/table sources committed with a tag or Zenodo snapshot if allowed.

Dependencies: Phase 1 frozen spec; pydicom (or equivalent) on execution environment.

# Phase 3 — dcm2niix batch proof (required for v1; not full BIDS)

Goal: second core empirical outcome alongside DBI — standard DICOM→NIfTI ingest stress test on the cohort. Full BIDS conversion (e.g., HeuDiConv / dcm2bids) and bids-validator correlation remain future work (Phase 8). Discussion may motivate DBI as easing eventual BIDS setup.

| Activity | Owner | Deliverable / output |
| --- | --- | --- |
| Pin tool versions (e.g., dcm2niix) and document CLI | Team + AI-assisted | Methods paragraph + environment file |
| Batch convert sample or full cohort; capture stderr/stdout and exit codes | Team run + AI-assisted scripts | conversion_log.csv |
| Define pass/fail (e.g., NIfTI exists, no fatal error, warning budget) | Team | Rubric in supplement |
| Cross-tab pass/fail × scanner cluster × modality heuristic | AI-assisted | Table 2 + optional Figure 2 |

Exit criteria: Table 2 (and optional Figure 2) ready for manuscript — required for v1 submission package.

Dependencies: software installed on cluster; legal to run conversion on data.

# Phase 4 — Optional: validation subset with human labels

Goal: report accuracy/precision of automated series-role classification (if claimed).

| Activity | Owner | Deliverable / output |
| --- | --- | --- |
| Sample 20–50 series stratified by scanner | Research team | Spreadsheet: path, true_role, notes |
| Compare rule-based or ML classifier to labels | AI-assisted | Confusion matrix, accuracy, kappa |
| Revise rules if systematic errors found | Team + AI-assisted | DBI v1.1 or classification appendix |

Exit criteria: supplement table or main text paragraph; or phase skipped if not a claim.

# Phase 5 — Manuscript and supplement

| Activity | Owner | Deliverable / output |
| --- | --- | --- |
| Introduction: problem, gap vs BIDS/DICOM/harmonization, contributions | AI-assisted draft + team rewrite | intro.docx / .tex |
| Methods: cohort, scanner groups, DBI definition, audit software, statistics | AI-assisted + team | methods section |
| Results: align every claim to Figure/Table | AI-assisted + team | results section |
| Discussion: limitations (N, single archive), related work, future multi-site | AI-assisted + team | discussion section |
| Supplement: SOP excerpts from AI_Ready_Acquisition_*, full tag list, extra figures | AI-assisted + team | supplement.pdf |

Exit criteria: full draft v1.0 internally circulable.

# Phase 6 — Reproducibility and data/code packaging

| Activity | Owner | Deliverable / output |
| --- | --- | --- |
| README: how to install, configure paths, rerun tables (no raw data if policy forbids) | AI-assisted | README.md |
| License and citation file for code | Research team | LICENSE, CITATION.cff optional |
| Archive snapshot (Git tag, Zenodo, institutional repo) per sharing tier | Research team | DOI or internal accession ID |

Exit criteria: reproducibility statement text for manuscript matches actual availability.

# Phase 7 — Internal review, submission, revision

| Activity | Owner | Deliverable / output |
| --- | --- | --- |
| Coauthor review rounds | All authors | Tracked comments resolved |
| Graphical abstract and highlights (NeuroImage) | Team | Portal-ready assets |
| Cover letter emphasizing novelty and scope | Team + AI-assisted draft | PDF |
| Submit to NeuroImage | Corresponding author | Submission ID |
| Respond to reviewers | Team + AI-assisted | Point-by-point + revised draft |

Exit criteria: acceptance or resubmission plan documented.

# Phase 8 — Future work (post-v1 publication)

Not part of the first NeuroImage submission timeline. After a frozen de-identified cohort and stable DBI definition, pursue: (1) versioned BIDS conversion recipe (HeuDiConv / dcm2bids or equivalent) per scanner cluster; (2) run bids-validator on resulting layouts; (3) test whether higher DBI predicts fewer errors/warnings or lower manual curation burden.

Deliverable: second paper or major revision extension + open-sourced BIDS heuristics.

Dependency: sub-* layout and documented mapping from XNAT-style series names to BIDS entities.

# Suggested timeline (indicative)

Adjust to FTE and cluster access. Parallel tracks: Phase 1 can start drafting while Phase 0 finalizes if team agrees provisional outcome A.

| Phase | Weeks (indicative) | Notes |
| --- | --- | --- |
| 0 Scope lock | 1 | Blocking for everything else |
| 1 DBI v1 spec | 1–2 | Overlaps with early coding sketch |
| 2 Audit + Fig1/Table1 | 2–4 | Largest engineering block |
| 3 dcm2niix proof | 1–3 | Required; can parallel writing after Phase 2 |
| 4 Human labels | 1–2 | Optional; can sample during Phase 2 QC |
| 5 Manuscript v1 | 2–4 | Start prose once Table 1 exists |
| 6 Repro package | 1 | Often during revision |
| 7 Submit + revise | 8–20+ | Journal-dependent |
| 8 BIDS + validator (future) | TBD | Separate milestone after v1 paper |

# Risk register (short)

Policy change forbids public code → Plan B: aggregate-only supplement + institutional code on request.

DICOM read failures on subset → Document exclusion rule and sensitivity analysis.

Sparse modality (e.g., BOLD) → Frame as illustrative case study; do not overclaim N.

Reviewer demands second cohort → Discuss public subset replication or limit scope in revision.

# Document control

Version: 1.2. v1 scope locked: DBI + dcm2niix only; BIDS/bids-validator → Phase 8. Update dates/owners in Word as needed.